## Sheet1
Request Date | Delivery Date | Targeted Delivery Date | Eng Number | Code | Revison | Client | Site Information | FA Number | Result | Revenue | Project Type | PACE Number | Internal Client | Status | Team Member | Additional Notes | PO Contact Information | PO issued | PO Received | Week Complete | Month Complete | Year Complete
2017-03-24 | 2017-03-27 |  | 10002 | RIG | 1 | City | Class IV Rigging Plan | 2297937 | PASS | 866 | 1805 |  | JH | SENT TO CLIENT | RM |  |  |  |  | 13 | 3 | 2017
2017-04-04 |  |  | 10004 | SAR | 1 | Safety | Structural Analysis - Specialty |  |  | 0 | Waivers |  | CI | CANCELLED | TBD | Awaiting mapping
2017-04-26 | 2017-05-05 |  | 10007 | SAR | 1 | Isle of Palms | Structural Analysis |  | FAIL | 2000 | 1805 |  | MK | SENT TO CLIENT | BM |  |  |  |  | 18 | 5 | 2017
2017-04-26 | 2017-07-06 |  | 10007 | MOD | 1 | Isle of Palms | Water Tank Modification and Passing Analysis |  | PASS | 750 | 1805 |  | MK | SENT TO CLIENT | BM | Awaiting Input: On Hold waiting to direction from Andy Tillman on replacement part. Sent to Utility Service for approval, 6/22. Sent signed copies 7/6 to Brad for Utiltiy Service review. |  |  |  | 27 | 7 | 2017
2017-08-24 | 2017-08-30 | 2017-08-31 | 10007 | MOD | 2 | Isle of Palms | IOPWSC 150K Modifications |  | Pass | 375 | 1805 |  | BT | SENT TO CLIENT | BM | 10007-MOD2 |  |  |  | 35 | 8 | 2017
2017-04-27 | 2017-05-17 | 2017-05-31 | 10008 | SAR | 1 | TowerCo | High Capex Guyed Tower |  | FAIL | 1000 | 1805 |  | SR | SENT TO CLIENT | JH |  |  |  |  | 20 | 5 | 2017
2017-04-28 | 2017-06-05 | 2017-06-08 | 10009 | SAR | 1 | AT&T | Water Tank Analysis | 10129890-DUBOIS |  | 4900 | 1805 |  | CRM | SENT TO CLIENT | BM | Confirmed full structural analysis required. Mapping received 6/1. |  |  |  | 23 | 6 | 2017
2017-05-01 | 2017-05-03 |  | 10010 | RIG | 1 | SBA | Class IV Rigging Plan |  |  | 866 | 1805 |  | RG | SENT TO CLIENT | RM |  |  |  |  | 18 | 5 | 2017
2017-05-09 | 2017-05-12 |  | 10013 | SAR | 1 | AT&T | Structural Analysis - ID | 10130457-MONIDA | PASS | 1400 | 1805 |  | CRM | SENT TO CLIENT | JH | Confirmed full structural analysis required |  |  |  | 19 | 5 | 2017
2017-09-14 | 2017-10-05 | 2017-10-04 | 10015 | SAR | 1 | AT&T | GASC_GRVCL_002 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-118 9.29 Analyze existing wood pole. If fails propose new wood pole. |  |  |  | 40 | 10 | 2017
2017-09-14 | 2017-10-05 | 2017-10-04 | 10015 | SAR | 1 | AT&T | GASC_GRVCL_007 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-123; 9.13 Duke Energy owned hold 9.29 Actually AT&T owned. 9.29 Replace existing utility pole with new wooden pole. Existing loading to be transferred to new pole plus new equipment. |  |  |  | 40 | 10 | 2017
2017-09-14 | 2017-10-06 | 2017-10-05 | 10015 | SAR | 1 | AT&T | RCKHL_001 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-25 | SK | 2017-09-18 | No | 40 | 10 | 2017
2017-09-14 | 2017-10-06 | 2017-10-05 | 10015 | SAR | 1 | AT&T | RCKHL_002 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-26 | SK | 2017-09-18 | No | 40 | 10 | 2017
2017-09-14 | 2017-10-06 | 2017-10-05 | 10015 | SAR | 1 | AT&T | RCKHL_003 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-27 | SK | 2017-09-18 | No | 40 | 10 | 2017
2017-09-14 | 2017-10-06 | 2017-10-05 | 10015 | SAR | 1 | AT&T | RCKHL_004 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-28 | SK | 2017-09-18 | No | 40 | 10 | 2017
2017-09-14 | 2017-10-06 | 2017-10-05 | 10015 | SAR | 1 | AT&T | RCKHL_005 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-29 | SK | 2017-09-18 | No | 40 | 10 | 2017
2017-09-29 |  | 2017-10-05 | 10015 | SAR | 1 | AT&T | RGSC_GRVGV_008 |  |  | 114.67 | 1802 |  | MA | CANCELLED |  | A&E Number 0207014001-8 9.29 Await PCD w/ light detail replacement.
2017-09-14 | 2017-10-06 | 2017-10-05 | 10015 | SAR | 1 | AT&T | RCKHL_006 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-30 | SK | 2017-09-18 | No | 40 | 10 | 2017
2017-09-14 | 2017-10-06 | 2017-10-05 | 10015 | SAR | 1 | AT&T | RCKHL_007 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-31 9.29 RRUs 2203 placed closer to antenna. | SK | 2017-09-18 | No | 40 | 10 | 2017
2017-09-29 |  | 2017-10-05 | 10015 | SAR | 1 | AT&T | RGSC_GRVGV_011 |  |  | 114.67 | 1802 |  | MA | CANCELLED |  | A&E Number: 0207014001-11 9.29 Await PCD w/ light detail replacement.
2017-09-14 | 2017-10-06 | 2017-10-05 | 10015 | SAR | 1 | AT&T | RCKHL_008 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-32 | SK | 2017-09-18 | No | 40 | 10 | 2017
2017-09-14 | 2017-10-06 | 2017-10-05 | 10015 | SAR | 1 | AT&T | RCKHL_009 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-33 9.29 RRUs 2203 placed closer to antenna. | SK | 2017-09-18 | No | 40 | 10 | 2017
2017-09-14 | 2017-10-06 | 2017-10-05 | 10015 | SAR | 1 | AT&T | RCKHL_010 |  |  | 114.67 | 1802 |  | MA | SENT TO CLIENT | AWM | A&E Number: 0207014001-34 | SK | 2017-09-18 | No | 40 | 10 | 2017